## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Research and making decision | 1 | 2022-04-29 | I was reading and going through different algorithms to find which one sounds most appealing to me.
Setting up and generating the grid | 2 | 2022-04-30 | In order to start working on the algorithm, I needed to create a grid with walls. I wanted to do everything in 3D. I prepared Unity for that. Created the 3D wall with 1x1 for the maze. Created the plane. Wrote successfully a code, which created a grid.
UI for changing the maze size | 1 | 2022-04-30 | Added two input boxes (for height and width) for the maze size and a button for generating the maze. Now user is able to choose the maze size and after clicking "Generate" button, it will generate a maze. Every time the button is pressed, the program will delete the previous maze and will create a new one. Created script for getting input values, changed maze grid generation script to adapt to input size, added functionality for "Generate" button.
Working on the algorithm | 3 | 2022-05-01 | Started working on the algorithm. By the end of the working time I was left with problem - algorithm did not go through the whole maze and ended up with endless loop.
Working on the algorithm | 2 | 2022-05-02 | Managed to fix the problem and finish the algorithm. Now everything works without errors, but realized that when the size is 50x50 or over, the generation is really slow. After some time later, managed to find the problem and now it was working ok.
Fixing the generation speed | 2 | 2022-05-03 | Trying to figure out a method that allows it to generate bigger mazes faster. Made multiple attempts to that, but non of them made anything better - so I left the generation as it was.
Added designed walls | 2 | 2022-05-04 | Made four wall designs and changed the code so that it will choose a random wall design in order to make the maze look more interesting and random.
Code-checkup + small but fixes | 1 | 2022-05-04 | Looked over the code. Deleted unnecessary things. Added more comments where needed. Changed the names where necessary. Also fixed smaller bugs that came up.
Plane size matching the maze size, UI design, error message | 1 | 2022-05-05 | No matter of the maze size, plane will always be the same size. Added UI design for input fields, button, text size, colours. Added check for input fields so that it is only possible to add values between 1 and 250. If anything else is added - error message is displayed.
Device/screen size check + show full maze on screen | 2 | 2022-05-06 | Program check the size of the screen to know what camera placement and UI size to use. Now should be like that not matter the maze size or screen, maze will always be fully on screen from up to down view.
Added more wall designs | 1 | 2022-05-08 | Added four more wall designs to have more variety.
Added gameplay | 1 | 2022-05-08 | After generating the maze, a play button appears. Now the user is able to click the play button. After clicking the button, player is taken to a 3D FP view. Tried to add player movement, but did not get it to work well. Also, there were a problem that camera saw through the walls. | X
Finishing the gameplay mode | 3 | 2022-05-10 | After struggling with a lot of weird problems with the movement I finally was able to have somewhat movement - it is definitely not perfect, but ok to use. Also, fixed the problem that the user was able to see through walls. Added "Back" button, so that when the player wants to generate the maze again, it will go back to generation mode. | X
Lights + fog | 1 | 2022-05-11 | Tried to make lighting of the game mode better, but with not much experience with the light, did not know how to achieve wanted. Added fog for the gameplay mode. | X
Testing | 1 | 2022-05-13 | Tried to test the gameplay mode and generating different sizes. Run into a problem that with too big maze, the gameplay mode is extreamly slow because of the amount of things used in the scene. FPS goes really high. | X
Making two modes | 1 | 2022-05-13 | I had to make two modes in order to demonstrate more successfully my algorithm working and the design part I did. | X
Total amount of hours | 18